## Harweel HSE Plan 2009
|  |  | Harweel Phase 2AB project 2009 HSE Plan | [9 empty] | Rev: 0 9/March/09
|  | Accountable | RESPONSIBLE (Make it Happen) | [11 empty] | Reviews
|  | LT Sponsor | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Actual | Target | Q1 | Q2 | Q3 | Q4
Strategic Management
1 | Project Manager Contractor Forum | OSH |  | OSHC1 |  |  | OSHC2 |  |  | OSHO2 |  |  |  | 3
2 | Senior Managers (LT) Walkthrough inspection | OSHC | OSH | OSHC | OSHO | OSHI | OSHS | OSHH | OSHQ | OSH | OSHC | OSGO |  | 10
3 | Managers and Supvr Attend New Worksite Hazard management Training as per Corporate MUST Win Project | OSH OSHC: OSH; OSHC1 OSHI: LT; OSHC2 OSHH: LT; OSHO2 OSH: LT; OSHO2 OSGO: LT |  | 4
4 | PDO HSE Monthly presentation with performance analysis MAF & SITE | OSHH | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 |  | 10
5 | Fountain System Close Out Check and analysis | OSH OSHC: OSHH; OSH OSH: OSHH3; OSHC1 OSHI: OSHH3; OSHC2 OSHQ: OSHH3; OSHO2 OSGO: OSHH3 |  | 4
6 | Action Tracking Register (ATR) Review | OSH | OSHC1 | OSHC2 | OSHC1 | OSHC2 | OSHC1 | OSHC2 | OSHO/2 | OSHC1 | OSHC2 | OSHO/2 |  | 10
7 | Harweel Safety Day | OSH OSHC: OSHC; OSHC1 OSHO: Plan OSHC1/2; OSHC2 OSHQ: Execute OSHH3 |  | 1
8 | Complete HSE Competence Assessment for CH/CSRs + Level 2 HSE Critical positions | OSH OSHC: OSHH; OSHC1 OSHC: OSHH3; OSHC2 OSHQ: OSHH3 |  | 2
9 | HSE Professionals TEAM workshop Site | OSH OSHC: OSHH; OSHC1 OSHC: OSHH3; OSHC2 OSHQ: OSHH3 |  | 2
10 | Site Golden Rules Session 2009 (1 per month) | OSHH | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 |  | 10
11 | Complete Mandatory Training Review all staff | OSH OSHC: OSHH; OSHC1 OSHO: OSHC1; OSHC2 OSHQ: OSHC2 |  | 2
12 | DDC/1 for family members (2 monthly promotion ) | OSH OSHC: OSHH; OSH OSH: OSHH; OSHC1 OSHO: OSHH; OSHC2 OSHS: OSHH; OSHC2 OSHQ: OSHH; OSHO2 OSHC: OSHH |  | 5
13 | HSEMS and Pre-Start up audit | OSH OSHC: OSHO; OSHC1 OSHO: HSEMS OSHH; OSHC2 OSHS: PrePSU OSHO2; OSHC2 OSHQ: Sweet PSU OSHO2; OSHO2 OSGO: Sour PSU OSHO2 |  | 4
Health
14 | SP1230 + 1231 Audit/Review (Med-OCC Health) | OSH OSHC: OSHI; OSHC1 OSHC: OSHH31; OSHO2 OSHC: OSHH31 |  | 2
15 | HRA for OSHO Positions in place | OSH OSHC: OSHO; OSHC2 OSHS: OSHO1; OSHO2 OSGO: OSHO1 |  | 2
16 | SP1233 Campaign (Smoking/Drugs/Alcohol) | OSH OSHC: OSHS; OSHC1 OSHO: OSHH31; OSHC2 OSHQ: OSHH31 |  | 2
17 | SP1232 Public Health /Catering Audit | OSH OSHC: OHSD; OSH OSH: OSHH3 3rd party; OSHO2 OSHC: OSHH31 |  | 2
Safety
18 | SP2000 & 2001 Audit (Road Safety) | OSH OSHC: OSHH; OSHC1 OSHC: OSHC2; OSHO2 OSH: OSHC1 |  | 2
19 | PTW Change over plan issued | OSH OSHC: OSHO; OSHC1 OSHO: OSHO2 |  | 1
20 | PTW Audit (PR1171/1172, PR1078-H2S, PEC system) | OSH OSHC: OSHO; OSH OSH: OSHH3; OSHC2 OSHH: OSHO2 |  | 2
21 | NDT Audit incorporating SP1237 ionising radiation | OSH OSHC: OSHQ; OSHC1 OSHC: OSHQ1; OSHC2 OSHQ: OSHQ1 |  | 3
22 | SP1257 Working at Height Audit | OSH OSHC: OSHC; OSHC1 OSHO: OSHC1/2 |  | 1
23 | SP1256 Industrial Safety Audit | OSH OSHC: OSHC; OSHC1 OSHI: OSHC1/2 |  | 1
24 | Pressure/Leak Testing Audit | OSH OSHC: OSHC; OSHC1 OSHC: OSHC2; OSHC2 OSHQ: OSHO2 |  | 1
25 | Implementation of Technical Integrity Framework Review/Verification | OSH OSHC: OSHE; OSHC1 OSHC: OSHI3; OSHC2 OSHS: OSHI3; OSHO2 OSH: OSHI3 |  | 3
26 | PR1508 Mechanical Lifting Audit | OSH OSHC: OSHS; OSHC1 OSHO: OSHC1; OSHO2 OSH: OSHO2 |  | 2
Environment/SD
27 | SP1009/11/12/13 Waste Manag/Flora/Land/Permits | OSH OSHC: OSHC; OSH OSH: OSHH2; OSHC1 OSHI: OSHH2; OSHC2 OSHQ: OSHH2; OSHO2 OSGO: OSHH2 |  | 1
28 | SP1194 Chemical Management | OSH OSHC: OSHO; OSHC1 OSHO: OSHC1/2; OSHC2 OSHQ: OSHO2 |  | 1
Emergency Preparedness
29 | Emergency Response Audit (review Oct/08 audit) Review PDO/PEC Emergency Resp Plan allignment | OSH OSHC: OSHO; OSHC1 OSHC: OSHH3; OSHO2 OSHC: OSHO2 |  | 2
30 | Offices emergency exercise (Site and MAF) | OSH OSHC: OSH; OSH OSH: OSHC1; OSHC1 OSHI: OSHC2; OSHC2 OSHH: OSHQ; OSHO2 OSH: OSHC1; OSHO2 OSGO: OSHO |  | 5
31 | Camp emergency exercise | OSH OSHC: OSHC; OSHC1 OSHC: OSHC2; OSHC1 OSHI: OSHC1; OSHC2 OSHH: OSHO; OSHO2 OSH: OSHC2; OSHO2 OSGO: OSHQ |  | 5
32 | Site ISBL emergency exercise | OSH OSHC: OSHH; OSHC1 OSHO: OSHH; OSHC2 OSHS: OSHC; OSHC2 OSHQ: OSHO; OSHO2 OSHC: OSHO |  | 4
33 | Site OSBL emergency exercise | OSHO | OSHC2 | OSHH3 |  | OSHC1 |  | OSHO |  | OSHO |  | OSHH3 |  | 6
34 | Road emergency exercise | OSH OSHC: OSHQ; OSH OSH: OSHH3; OSHC1 OSHO: OSHH3; OSHC2 OSHS: OSHH3; OSHC2 OSHQ: OSHO; OSHO2 OSHC: OSHO |  | 5
35 | Industrial Area emergency exercise | OSH OSHC: OSHS; OSH OSH: OSHO; OSHC1 OSHO: OSHC1; OSHC2 OSHS: OSHC2; OSHC2 OSHQ: OSHQ; OSHO2 OSHC: OSHH |  | 5
36 | Medical emergency exercise | OSHI | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 |  | 10
LAGGING INDICATORS
37 | LTIF: target below 0.5 | OSH OSHC: OSHH; OSH OSH: OSHH3; OSHC1 OSHI: OSHH3; OSHC2 OSHQ: OSHH3; OSHO2 OSGO: OSHH3 |  | 0.5
38 | TRCF: target below 6.0 | OSH OSHC: OSHH; OSH OSH: OSHH3; OSHC1 OSHI: OSHH3; OSHC2 OSHQ: OSHH3; OSHO2 OSGO: OSHH3 |  | 6
39 | RTAF: target below 2.5 | OSH OSHC: OSHH; OSH OSH: OSHH3; OSHC1 OSHI: OSHH3; OSHC2 OSHQ: OSHH3; OSHO2 OSGO: OSHH3 |  | 2.5
LEADING INDICATORS
40 | Number of STOP Cards | OSH | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 2000
41 | Health Awareness Sessions | OSH OSHC: OSHI; OSHC1 OSHC: OSHH3; OSHC1 OSHI: OSHH3; OSHC2 OSHH: OSHH3; OSHO2 OSH: OSHH3; OSHO2 OSGO: OSHH3 |  | 5
42 | Environmental Awareness Sessions | OSH OSHC: OSHD; OSHC1 OSHO: OSHH2; OSHC2 OSHH: OSHH2; OSHO2 OSHC: OSHH2 |  | 3
43 | PDO Driving Safety Monthly Forum (Site and MAF) including specific dates for MSE Forums | OSHH | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 |  | 10
44 | Site Team Leaders TBT Attendance /JHA/PTW Sampling/Slips and Trips/Fire Safety | OSHC | OSHC1 | OSHC2 | OSHO2 | OSHC1 | OSHC2 | OSHO2 | OSHC1 | OSHC2 | OSHO2 | OSHC1 |  | 100
45 | Roll-out sessions Operations Safety Case | OSH OSHC: OSHO; OSH OSH: OSHO5; OSHC1 OSHC: OSHO5 |  | 2
| Author Accepted: OSHH3 | OSH OSH: Note: detailed plans are kept on site by OSHH/3 for 1) Health promotion activities 2) Drive to Survive activities
Verifiy: OSHH
Project Manager: OSH