## OSH HSE Plan 2010
|  | Harweel Phase 2AB project 2010 HSE Plan: OSH & OSGO | [11 empty] | Rev: 0 27/Jan/2010
|  | Action Party | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Comments
Strategic Management
1 | Project Manager - HSE plan launch/review | OSH OSGO | Feb: HSE Plan Launch; Aug: HSE Review
2 | Senior Managers (LT) Walkthrough inspection (Inspection report deliverd to OSHH/3) | LT | OSHH | OSH | OSHC | OSHE | OSHS | OSGO | OSGOH | OSH | OSHC | OSHE | OSGO | OSGOH
3 | Senior Managers attend CEO HSE Conference | OSH OSGO LT: LT; HSE Plan Launch OSHE: 28 April; HSE Review OSGOH: 2010-12-01
4 | HSE Training Compliance Review OSGO staff (PDO must win - new HSE training scales) | OSH OSGO LT: OSGOH; HSE Plan Launch OSHC: OSGOH 50% compl; HSE Review OSHC: OSGOH 100% compl
5 | Site HSE Monthly presentation with performance analysis (at MAF by OSHH in TL meeting) | OSHH/3 + | OSHC1 | OSHC2 | OSHC5 | OSHC1 | OSHC2 | OSHC5 | OSGOH | OSGOH | OSGOH | OSGOH | OSGOH | OSGOH
6 | STOP Refresher Training (Book 5) including physical site tours | OSH OSGO LT: OSHH/3; HSE Plan Launch OSHE: OSHH31; HSE Review OSHE: OSGOH/5
7 | Action Tracking Register (ATR) Review (PEC list and a to be developped OSGOH list) | OSH OSGO LT: OSHC OSGOH; OSH OSGO OSHH: OSHH; HSE Plan Launch OSHC: OSHC1; HSE Plan Launch OSHS: OSHC2; HSE Plan Launch OSGOH: OSHC5; HSE Review OSHC: OSHC5; HSE Review OSGO: OSGOH
8 | Harweel Safety Day (Goal Zero) | OSH OSGO LT: OSHC; HSE Plan Launch OSGO: Date tbc
9 | Complete HSE Competence Assessment for Level 2 HSE Critical positions in OSGOH | OSH OSGO LT: OSGOH; HSE Plan Launch OSGO: 50%; HSE Review OSHE: 100%
10 | HSEMS preparedness Pre-Start Up audit (dates to be revised as per actual progress) | OSH OSGO LT: OSHC/5; HSE Plan Launch OSH: Revw PSU Readiness; HSE Plan Launch OSHC: Sweet PSU; HSE Review OSH: Sour PSU
11 | Site TL execute a: JHA /PTW Sampling/Slips and Trips/Fire Safety/ walkabouts/TRIC | OSHC OSGOH | OSHC1 | OSHC2 | OSHC5 | OSHQ1 | OSHC51 | OSGOH | OSHC5 | OSHC51 | OSGOH/1 | OSGOH/4 | OSGOH | OSGOH/1
12 | Commissiong/Operations Safety Case implemenation/action review | OSH OSGO LT: OSHC/5 OSGOH; HSE Plan Launch OSHC: OSHC5 Comm Case; HSE Review OSHE: OSGOH Ops Case
13 | HSE Corporate Joint Management Inspections | OSH OSGO LT: OSGO; HSE Review OSGO: XD
Health
14 | SP1230 + 1231 Audit/Review (Med-OCC Health) | OSH OSGO LT: OSHH3; HSE Plan Launch OSHC: OSHH3; HSE Review OSHE: Review March audit
15 | HRA for all OSGHO Positions in place | OSH OSGO LT: OSGOH; HSE Plan Launch OSHE: 50%; HSE Review OSH: 100%
16 | Third Party SP1232 Public Health /Catering Audit (PEC and PDO camps) | OSH OSGO LT: OSHH3; HSE Plan Launch OSHE: ALL CAMPS
17 | O/H Awareness Sessions | OSH OSGO LT: OSHH3; HSE Plan Launch OSH: MSE /23; HSE Plan Launch OSHE: HEAT STRESS; HSE Plan Launch OSGO: FATIGUE; HSE Review OSHE: Manual Lifting
18 | Fitness to Work Medical Assesemts for OSGOH staff completed | OSH OSGO LT: OSGOH; HSE Plan Launch OSH: 25%; HSE Plan Launch OSHE: 50%; HSE Plan Launch OSGO: 75%; HSE Review OSH: 100%
Safety
15 | SP2000 & 2001 (Road Safety Blitz) Last week of Feb/First week March | OSH OSGO LT: OSHH; HSE Plan Launch OSH: Road Safety Blitz (2 week prgrm SP2000/01 aspects); HSE Review OSHE: Review
16 | PTW Audit (PR1172) | OSH OSGO LT: OSGOH; HSE Plan Launch OSHE: Level 1 Audit; HSE Review OSHE: Level 2 Audit
17 | TRIC for Operations (PDO must win) | OSGOH |  | Roll out | Observation | Observation | Observation | Observation | Observation | Observation | Observation | Observation | Observation | Observation
18 | Hazard Awareness Sessions (PDO must win) | OSH OSGO LT: OSHH; HSE Plan Launch OSH: Roll out; HSE Plan Launch OSHC: session; HSE Plan Launch OSHS: session; HSE Plan Launch OSGOH: session; HSE Review OSHC: session; HSE Review OSGO: session
19 | Implementation of Technical Integrity Framework Review/Verification | OSH OSGO LT: OSHI; HSE Plan Launch OSH: TIHB Ass & PSU Rvw; HSE Plan Launch OSHC: Sweet PSU &TIHB; HSE Review OSH: Sour PSUA & TIHB
20 | Site hazards activitry sampling (mini audit) Hydrotesting/Scaffold/Coms Activities/Chem | OSH OSGO LT: OSHC OSGOH; HSE Plan Launch OSH: OSHC1; HSE Plan Launch OSHE: OSHC2; HSE Plan Launch OSGO: OSHC5; HSE Review OSH: OSHC5; HSE Review OSHE: OSHGOH; HSE Review OSGOH: OSHGOH
Environment/SD
21 | SP1009/11/12/13 Waste Manage/Flora/Land/Permits (requirement EIA) | OSH OSGO LT: OSGOH OSHH; HSE Plan Launch OSHC: OSHH/3; HSE Plan Launch OSGO: OSGOH; HSE Review OSHC: OSGOH; HSE Review OSGOH: OSGOH
22 | Environmental Awareness Sessions | OSH OSGO LT: OSHH; HSE Plan Launch OSHC: Env Day MSE Mar 7; HSE Review OSGO: OSHH
23 | SP1194 Chemical Management Committee Meeting (and action follow up) | OSH OSGO LT: OSHC/5 OSGOH; OSH OSGO OSHH: OSHH3; HSE Plan Launch OSHC: OSHC/5; HSE Plan Launch OSHS: OSHC/5; HSE Plan Launch OSGOH: OSGOH; HSE Review OSHC: OSGOH; HSE Review OSGO: OSGOH
Emergency Preparedness
24 | Emergency Response Preparedeness Review | OSH OSGO LT: OSHC OSGOH; HSE Plan Launch OSHE: OSHC5; HSE Review OSH: OSGOH
25 | Chemical Spill emergency exercise | OSH OSGO LT: OSHC OSGOH; HSE Plan Launch OSHC: OSHC5; HSE Review OSHC: OSGOH
26 | Site Offices emergency exercise | OSH OSGO LT: OSHC OSGOH; HSE Plan Launch OSH: OSHH3; HSE Plan Launch OSHS: OSGOH; HSE Review OSH: OSGOH; HSE Review OSGO: OSGOH
27 | Camp emergency exercise (PEC & PDO) | OSH OSGO LT: OSHC OSGOH; HSE Plan Launch OSHC: OSHC/1/2 & OSHC5; HSE Review OSH: OSHC/1/2 & OSHC5
28 | Site (ISBL/OSBL) emergency exercise | OSH OSGO LT: OSHC OSGOH; HSE Plan Launch OSH: OSHC1; HSE Plan Launch OSHS: OSHC2; HSE Review OSH: OSHC5; HSE Review OSGO: OSGOH
29 | Road emergency exercise | OSH OSGO LT: OSHC OSGOH; HSE Plan Launch OSHC: OSHC2; HSE Review OSHE: OSGOH
30 | N2/Helium emergency exercise | OSH OSGO LT: OSHC/1; HSE Plan Launch OSH: Weather-ford
31 | Medical emergency exercise (PEC and PDO clinics) | OSH OSGO LT: OSHH/3 MCN/11H
Performance INDICATORS
32 | LTIF: target below 0.5 (PDO target: 0.53) | OSH OSGO LT: OSHH
33 | TRCF: target below 4.5 (lower than 2009 actual) | OSH OSGO LT: OSHH
34 | RTAF: target below 2.3 (lower than 2009 actual) | OSH OSGO LT: OSHH
35 | Number of STOP Cards: number | OSH | 200 | 200 | 200 | 200 | 150 | 150 | 150 | 150 | 100 | 100 | 100 | 100
Note on I12: mu53531: depending on Corp Dates

## Hrw 2009 HSE Plan-Dec09 review
| Year End Final Review (5/Jan/2010) |  | Harweel Phase 2AB project 2009 HSE Plan | [9 empty] | Rev: 0 9/March/09
|  | Accountable |  |  |  | RESPONSIBLE (Make it Happen) | [8 empty] | Reviews
|  | LT Sponsor | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Actual | Target | Q1 | Q2 | Q3 | Q4 | Comm Dec-09 Review
Strategic Management
1 | Project Manager Contractor Forum | OSH |  | OSHC1 | [6 empty] | OSHC5 |  |  | 3 |  |  |  |  | Did not happen. Will re-plan to Q1
2 | Senior Managers (LT) Walkthrough inspection | OSHC | OSHC/H swap OSH | OSH swap OSHC | OSHI | OSHC | OSHH | OSH | OSHQ | OSH | OSHE | OSHC |  | 10 |  |  |  |  | Rinus with Jim
3 | Managers and Supvr Attend New Worksite Hazard management Training as per Corporate MUST Win Project | OSH | [11 empty] | 4 |  |  |  |  | 1 day CEO SLT atended, Supervisors Continues in 2010 | bar: OSHC; OSH; OSHC5 OSHC
4 | PDO HSE Monthly presentation with performance analysis MAF & SITE | OSHH | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 | OSHH OSHH/3 |  | 10
5 | Fountain System Close Out Check and analysis | OSHH | OSHH3 |  | OSHC: OSHH3; OSHQ: OSHH3; OSHC5 OSHC: OSHH3 |  | 4
6 | Action Tracking Register (ATR) Review | OSH | OSHC1 1wk April | OSHC2 | OSHC1 | OSHC2 | OSHH/3 | OSHH | OSHH | OSHC1 | OSHC2 | OSHC5 |  | 10
7 | Harweel Safety Day | OSHC |  |  | OSHI: Plan OSHC1/2; OSHH: Execute OSHH3 |  | 1
8 | Complete HSE Competence Assessment for CH/CSRs + Level 2 HSE Critical positions | OSHH |  | OSHH3 List | OSHC5 OSHC: OSHH3 |  | 2 |  |  |  |  | CH/CSR's completed Level 2 for OSGOH in 2010
9 | HSE Professionals TEAM workshop Site | OSHH |  | OSHH3 | OSHC5 OSHE: OSHH3 |  | 2
10 | Site Golden Rules Session 2009 (1 per month) | OSHH | OSHH3 8/Apr | OSHH3 | OSHH3 SLR Sess | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 |  | 10
11 | Complete Mandatory Training Review all staff | OSHH |  |  | OSHI: OSHC1; OSHQ: OSHC2 |  | 2 |  |  |  |  | Done by OSHH3 on site. OSGOH staff done.
12 | DDC/1 for family members (4 monthly promotion ) | OSHH | OSHH |  | OSHC: OSHH; OSH: OSHH |  | 5 |  |  |  |  | Reduced from 4 to 3
13 | HSEMS and Pre-Start up audit | OSGOH |  |  | OSHI: HSEMS OSHH; OSH: PrePSU OSHC5; OSHC5 OSHC: Sweet PSU OSHC5 |  | 4 |  |  |  |  | Project Slipped PrePSU/PSU S&S in 2010
Health
14 | SP1230 + 1231 Audit/Review (Med-OCC Health) | OSHI |  |  | OSHI: OSHH31 SP-1230; OSHC5 OSHC: OSHH31 |  | 2 |  |  |  |  | SP-1230 and Noise (1231) done
15 | HRA for OSGOH Positions in place | OSGOH |  |  | OSHQ: OSHO1; OSHC5 OSHC: OSHO1 |  | 2 |  |  |  |  | Not done: OSGOH move to 2010 OSHC activities: all in place
16 | SP1232 Public Health /Catering Audit | OHSD | OSHH3 3rd party |  | OSHQ: OSHH31 |  | 2 |  |  |  |  | HACCP training and audit by external party
17 | SP1233 Campaign (Smoking/Drugs/Alcohol) | OSHS |  |  | OSHI: OSHH31 Beat Heat; OSHC: OSHH31; OSHC5 OSHC: OSHH31 |  | 2 |  |  |  |  | Limited to poster campaign
Safety
18 | SP2000 & 2001 Audit (Road Safety) | OSHH |  | OSHC2 Done: May | OSH: OSHC1 |  | 2 |  |  |  |  | Intensive DtS and RSSTactivities have replaced this formal audit.
19 | PTW Change over plan issued | OSGOH |  |  | OSHH: OSHC5 |  | 1
20 | PTW Audit (PR1171/1172, PR1078-H2S, PEC system) | OSGOH | OSHH3 |  | OSHQ: OSHC5 |  | 2 |  |  |  |  | Moved from Aug to Sept
21 | NDT Audit incorporating SP1237 ionising radiation | OSHQ |  | OSHQ1 | OSHQ: OSHQ1 |  | 3
22 | SP1257 Working at Height Audit | OSHC |  |  | OSHC: OSHC1/2 |  | 1 |  |  |  |  | Moved from May to June
23 | SP1256 Industrial Safety Audit | OSHC |  |  | OSHC: OSHC1/2; OSHC5 OSHE: OSHH/3 |  | 1 |  |  |  |  | New audit added to Nov.
24 | Pressure/Leak Testing Audit | OSHC |  | OSHC2 | OSHC5 OSHE: OSHC5 follow-up |  | 1
25 | Implementation of Technical Integrity Framework Review/Verification | OSHE |  | OSHI3 | OSHH: OSHI3; OSH: OSHI3 |  | 3 |  |  |  |  | Statuus ?????
26 | PR1508 Mechanical Lifting Audit | OSHS |  |  | OSHI: OSHC151 UEC/14; OSH: OSHC5 |  | 2 |  |  |  |  | 1st week Nov by Kevin
Environment/SD
27 | SP1009/11/12/13 Waste Manag/Flora/Land/Permits | OSHC | OSHH2 |  | OSHC: OSHH2; OSHQ: OSHH2; OSHC5 OSHC: OSHH2 |  | 1
28 | SP1194 Chemical Management | OSGOH |  |  | OSHI: OSHC1/2; OSHC5 OSHE: OSHC5 Commit |  | 1 |  |  |  |  | OSHH/3 intiated Cehmical management committee with TOR. Audit moved to Feb/2009.
Emergency Preparedness
29 | Emergency Resp Audit (Oct/08 audit). Review PDO/PEC Emergency Resp Plan allignment | OSGOH |  |  | OSHI: Extra: Fire safety Extinguisher; OSHH: OSHH3 Emerg Resp Follow Up |  | 2 |  |  |  |  | OSGOH audit moved from Nov to March.
30 | Offices emergency exercise (Site and MAF) | OSH | OSHC1 Feb/09 |  | OSHH: OSHC2; OSH: OSHQ MAF; OSHQ: OSHC1; OSHC5 OSHC: OSGOH |  | 5 |  |  |  |  | Moved to Dec
31 | Camp emergency exercise | OSHC |  |  | OSHI: OSHC2; OSHC: OSHC1; OSH: OSHC2 Ldry Fire; OSHC5 OSHC: OSHQ PDO camp |  | 5
32 | Site ISBL emergency exercise | OSHH |  |  | OSHI: OSHH; OSHH: OSHC; OSHQ: OSGOH; OSHC5 OSHE: OSGOH Real Fire ISBL |  | 4
33 | Site OSBL emergency exercise | OSGOH | OSHC2 | OSHH3 | OSHC: OSHC1; OSH: OSHH3 H2S exerc; OSHC5 OSHE: OSHC/2 NDT on Zal; OSHC5 OSHC: OSHH3 H2S at Zal |  | 6
34 | Road emergency exercise | OSHQ | OSHH3 |  | OSHI: OSHH3; OSHH: OSHH3 Real event; OSHC5 OSHE: OSHH/3 Head On |  | 5
35 | Industrial Area emergency exercise | OSHS | OSGOH |  | OSHI: OSHC1 (Real); OSHH: OSHC2; OSH: OSHQ; OSHC5 OSHC: OSHH (Chem) |  | 5
36 | Medical emergency exercise | OSHI | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 | OSHH31 |  | 10
LAGGING INDICATORS
37 | LTIF: target below 0.5 | OSHH | 0.27 | 0.79 | 0.63 | 0.52 | 0.45 | 0.39 | 0.35 | 0.31 | 0.29 | 0.26 |  | 0.5
38 | TRCF: target below 6.0 | OSHH | 4.54 | 4.34 | 4.09 | 4.45 | 4.5 | 4.02 | 4.26 | 4.23 | 4.49 | 4.29 |  | 6
39 | RTAF: target below 2.5 | OSHH | 3.58 | 3.08 | 3.08 | 2.48 | 2.69 | 2.82 | 2.61 | 2.47 | 2.35 | 2.26 |  | 2.5
LEADING INDICATORS
40 | Number of STOP Cards | OSH | 399 | 518 | 552 | 341 | 495 | 353 | 393 | 306 | 643 | 334 |  | 2000
41 | Health Awareness Sessions | OSHI |  | OSHH3 | OSHC: OSHH3; OSH: OSHH3; OSH: OSHH3; OSHC5 OSHC: OSHH3 |  | 5
42 | Environmental Awareness Sessions | OSHD |  |  | OSHI: OSHH2 to June; OSH: OSHH2; OSHC5 OSHC: OSHH2 |  | 3 |  |  |  |  | Was planned for Sat/19. Became holiday. Will be done Jan return leave
43 | PDO Driving Safety Monthly Forum (Site and MAF) including specific dates for MSE Forums | OSHH | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 | OSHH3 UEP | OSHH3 | OSHH3 | OSHH3 |  | 10
44 | Site Team Leaders TBT Attendance /JHA/PTW Sampling/Slips and Trips/Fire Safety walkabouts | OSHC | OSHC1 | OSHC2 | OSHC2 | OSHC1 | OSHC2 | OSHC5 | OSHC1 | OSHC2 | OSHC5 | OSHC1 |  | 100
45 | Roll-out sessions Operations Safety Case | OSGOH | OSHO5 | OSHO5 | [9 empty] | 2
| Author Accepted: OSHH3 |  | Note: detailed plans are kept on site by OSHH/3 for 1) Health promotion activities 2) Drive to Survive activities
Verifiy: OSHH
Project Manager: OSH