## Slide 1
Screening Process is the first step in the Impact Assessment (IA) Process. The Screening Process checklist is to be filled at Identify & Assess phase for medium/major projects, and at or near the beginning of Select Phase for small projects, by the project team and re-visited at a later stage in case of changes in project (e.g. scope, location, etc).
The outcome of the Screening Report will determine the project category, identify any “showstoppers” for options being considered in terms of ESH (Environment, Social and Health) e.g. site selection, routing, equipment choice and hence the further environmental, Social and Health deliverables required for the project.
Screening Report checklist is not filled out early in the project implementation process. The Screening Report is usually filled out after concept/option is being selected and in some cases immediately before planned project operation, which disregards Environment, Social and Health (ESH) impacts from being part of the options evaluation.
The current Screening Report does not provide a holistic initial assessment that allows proper categorisation of the project. It does not cover Health aspects and has limited data on Environment and Social aspects. In many cases the Screening Report not filled out sufficiently due to lack of information and understanding of requirements. The current system is based on excel sheets. It lacks audit trail and result in inadequate management of information and lacks formal approval process particularly, in case of significant change of project scope.
Late completion of the Screening Report coupled with inadequate assessment, prevents projects from being timely and accurately categorized and may delay the delivery of Concept Selection Reports (CSRs) and project startup while waiting on environmental risk assessments to be completed (including permit application).
The major findings are:
The requirement and importance to fill out Screening Report is not clear to project team.
  Root Cause - DCAF doesn’t directly refer to I Screening Report as a required document.
Current Screening Report template is not readily available.
  Root Cause – MSE24 Environmental team must send template to concept engineer and MSE24 team is not always available.
Screening category decision does not always represent the current scope due to change of scope. There is no audit trail of Screening Report vs current project scope.
  Root Cause – No system exists for on line access to current Screening Report and no audit trail for decisions to change scope of work impacting Screening accuracy.
Repetitive meeting for getting required data, screening clarifications , decisions and alignment.
  Root Cause – New Concept Engineers are not effectively trained on project Environmental Screening requirements.
Environmental Team (projects support team) is not always able to respond quickly to concept engineers questions or to provide feedback on Screening Reports that have been submitted.
  Root Cause – (Mura) Number of requests for information is not equally distributed to the Environmental Team (projects support team).
Screening is not accurate with current Screening Report.
  Root Cause – Health is not included in current Screening Report, very limited data for Social, and insufficient data for Environment section. In addition, new projects requirements and new technologies are not captured in current Screening Report checklist.
Add clear statement about the Screening Report requirement into DCAF.
  Action #1 – Specify in DCAF the importance and requirement to fill out
  the Screening Report and add hyperlink for the Screening Report
  template in the DCAF Description sheet.
Provide on-line access for the Screening Report.
  Action # 2 – Same as Action #1
Have a shared on-line tool , where all Screening Reports can be saved in the tool and have on-line system/application to create Screening Report.
  Action #3 – Implement an online system to create and store the Screening Reports. After Completion/Approval of Screening Reports, make accessible (read only) to all concept/projects engineers.
Induction session on Environmental Requirements for new concept engineers.
  Action #4 – Develop new Induction training on screening requirements.
Equally distribute requests between Environmental team to provide a faster response to concept Engineers.
  Action #5 – online system is built in away to send Screening request to all MSE24 team (projects support team).
Update Screening Report for Environment, Social and Health sections.
  Action #6 – Update Screening Report with more descriptive required input for Project Date and Environmental Data and make it flexible to add comments/allow room for info. to be added and simplify the form.
  Action #7 – Update Screening Report to include Health section, more Environment and Social aspects and capture new projects requirements.
3 projects will pilot the enhanced Screening process and on line tool :
  Runib Flank Development (CSR : Jan. 2016)
  New Oil MSVs and Manifolds (CSR : Jan. 2016)
  Installation of Red Eye Meters in Rima (CSR : Jan. 2016)
At induction training, concept engineers agreed that all Screening Reports should be completed within 30 days after start of Select phase (for small projects). This is the KPI and standard that will be tracked on visual board.
(Last 6 Screening Report submissions, prior to project, exceeded standard by 78 up to 440 days)
Replication :
Not applicable. Will be implemented for all projects. Will occur immediately after implementing process upgrades from the pilot (Jan. 2016).
Training on Screening online : 3 session (completed), 1 more planned (22nd Dec.)
Self Training Slides (22nd Dec.)
Benefits :
- Accurate projects categorization.
- Ensure projects are not delayed due to time to conduct environmental impact assessments, i.e. starting Screening Process (including permit application).
- Enhance PDO’s reputation for fully considering Social, Health and Environmental aspects in projects.
Give easy Access to Screening Report template and easy audit trail of completed Screening Reports.
Eliminate IIE (Initial Impact Evaluation) external consultant report (for Category I & II projects), saving around OMR 10,000 (based on EMC/ODC contract agreement) for each study and ~ 2-3 months time of resources time.
Background
Current Conditions
Analysis
Countermeasure(s)
Pilot Plan & Results
Replication plan & Benefits
By end of 2015, deliver accurate projects Screening by :
Integrating Impact Assessment process early in the projects, through initiating Screening Process at or near the beginning of projects.
Incorporating it in evaluating feasibility of options (make relevant decisions at the right time), to make right choices, avoid project delivery delays, minimize costs, maintain reputation and ultimately meet business objectives.
Goal(s)
LSW plan will track KPI for all Screening Reports submissions.
Sustainability
A3: Improve Screening Process
Project Practitioner: Widad Al-Ajmi (MSE24S)
Project Champion: Mohammed Al-Shuayli (MSE2)
Line Manager : Mohamed Al-Salmani (MSEM)